**Alternative #1**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Task** | June 2011 | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. 2012 | Feb | Mar | Apr |
| Organize Resources |  |  |  |  |  |  |  |  |  |  |  |
| Hazard Analysis |  |  |  |  |  |  |  |  |  |  |  |
| Capability Assessment |  |  |  |  |  |  |  |  |  |  |  |
| Develop  Mitigation Strategy |  |  |  |  |  |  |  |  |  |  |  |
| Develop  Implementation Strategy |  |  |  |  |  |  |  |  |  |  |  |
| Write Plan |  |  |  |  |  |  |  |  |  |  |  |
| Public Review of Plan |  |  |  |  |  |  |  |  |  |  |  |
| Submit for Review |  |  |  |  |  |  |  |  |  |  |  |
| FEMA Approval |  |  |  |  |  |  |  |  |  |  |  |
| Formal Adoption |  |  |  |  |  |  |  |  |  |  |  |
| Planning Meetings |  | 2 | 1 | 1-2 | 1 | 1 |  |  |  |  |  |
| Public Meetings |  |  |  |  |  |  |  |  |  |  |  |

**Alternative #2**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Task** | June 2011 | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. 2012 | Feb | Mar | Apr-Jun |
| Organize Resources |  |  |  |  |  |  |  |  |  |  |  |
| Hazard Analysis |  |  |  |  |  |  |  |  |  |  |  |
| Capability Assessment |  |  |  |  |  |  |  |  |  |  |  |
| Develop Mitigation Strategy |  |  |  |  |  |  |  |  |  |  |  |
| Develop Implementation Strategy |  |  |  |  |  |  |  |  |  |  |  |
| Write Plan |  |  |  |  |  |  |  |  |  |  |  |
| Public Review of Plan |  |  |  |  |  |  |  |  |  |  |  |
| Submit for Review |  |  |  |  |  |  |  |  |  |  |  |
| FEMA Approval |  |  |  |  |  |  |  |  |  |  | June |
| Formal Adoption |  |  |  |  |  |  |  |  |  |  | June |
| Planning Meetings |  | 1 | 1 | 1 | 1 | 1 |  | 1 |  |  |  |
| Public Meetings |  |  |  |  |  |  |  |  |  |  |  |